## Claim
Progress claim and progress certificate, AS 4000 (New South Wales or Victoria)
Worked example from the sample contract. Replace the blue cells with your own job; every total is a formula and the due date on the Clock sheet moves with the claim date.
Contract | Brolga Creek Estate Stage 2 Roads and Drainage, Tallowwood, Queensland
Contract number | BCE-2026-011
Principal | Tallowwood Regional Council
Contractor | Ironbark Ridge Civil Constructions Pty Ltd
Superintendent | Awatere Consulting Engineers Limited
General conditions | AS 4000-1997
Currency | A$
Claim number | 2
Claim date (the date the claim is served) | 2026-04-25
Period up to and including | 2026-04-25
GST rate | 10%
Retention rate | 10% | of each certificate, to a cap of
Retention cap | 423000
Item | Description | Unit | Contract qty | Rate | Contract amount | Previously certified (percent) | Claimed to date (percent) | Claimed to date | Previously certified | This claim
1.01 | Establishment and disestablishment of site facilities | Item | 1 | 420000 | 420000 | 15% | 30% | 126000 | 63000 | 63000
1.02 | Site management, supervision and quality assurance | Item | 1 | 690000 | 690000 | 15% | 30% | 207000 | 103500 | 103500
2.01 | Bulk earthworks, cut to fill | m3 | 48000 | 16.5 | 792000 | 20% | 55% | 435600 | 158400 | 277200
2.02 | Cart surplus material to spoil | m3 | 9000 | 14 | 126000 | 20% | 55% | 69300 | 25200 | 44100
2.03 | Supply and place imported select fill | m3 | 6000 | 58 | 348000 | 20% | 55% | 191400 | 69600 | 121800
3.01 | Supply and lay 375 dia RCP class 4 including bedding | m | 900 | 410 | 369000 | 5% | 30% | 110700 | 18450 | 92250
3.02 | Supply and lay 600 dia RCP class 4 including bedding | m | 380 | 655 | 248900 | 5% | 30% | 74670 | 12445 | 62225
3.03 | Precast manholes 1050 dia complete | ea | 30 | 6900 | 207000 | 5% | 30% | 62100 | 10350 | 51750
4.01 | Supply and lay 150 dia PVC sewer including bedding | m | 1400 | 245 | 343000 | 0% | 10% | 34300 | 0 | 34300
4.03 | Sewer manholes 1050 dia complete | ea | 22 | 7300 | 160600 | 0% | 10% | 16060 | 0 | 16060
| Totals, the ten example rows |  |  |  | 3704500 |  |  | 1327130 | 460945 | 866185
Claimed to date (excl GST) | 1327130
Less previously certified | 460945
This claim (excl GST) | 866185
Retention held to date | 132713
Retention previously held | 46094.5
Retention this claim | 86618.5
Net this claim (excl GST) | 779566.5
GST | 77956.65
Amount claimed (incl GST) | 857523.15
Certificate due | 2026-05-09 | worked out by formula on the Clock sheet from the claim date in B12
Built by Alexios Kavallaris, civil engineer, from the Gnosis sample contract. gnosis.ltd

## Certificate
Progress certificate, AS 4000 and the Security of Payment Act (NSW 1999, Vic 2002)
The Superintendent's side. Each line starts equal to the claim; change a certified figure and write the reason beside it. Retention and GST follow the Claim sheet's terms.
Claim number | 2
Claim served | 2026-04-25
Certificate due (from the Clock sheet) | 2026-05-09
Reminder, two countable days before | 2026-05-07
Item | Description | Claimed to date | Certified to date | Difference | Reason where certified is less than claimed
1.01 | Establishment and disestablishment of site facilities | 126000 | 126000 | 0
1.02 | Site management, supervision and quality assurance | 207000 | 207000 | 0
2.01 | Bulk earthworks, cut to fill | 435600 | 435600 | 0
2.02 | Cart surplus material to spoil | 69300 | 69300 | 0
2.03 | Supply and place imported select fill | 191400 | 191400 | 0
3.01 | Supply and lay 375 dia RCP class 4 including bedding | 110700 | 110700 | 0
3.02 | Supply and lay 600 dia RCP class 4 including bedding | 74670 | 74670 | 0
3.03 | Precast manholes 1050 dia complete | 62100 | 62100 | 0
4.01 | Supply and lay 150 dia PVC sewer including bedding | 34300 | 34300 | 0
4.03 | Sewer manholes 1050 dia complete | 16060 | 16060 | 0
| Totals | 1327130 | 1327130 | 0
Certified to date (excl GST) | 1327130
Less previously certified | 460945
Certified this certificate (excl GST) | 866185
Retention held to date | 132713
Retention previously held | 46094.5
Retention released (enter an amount when retention is released) | 0
Retention this certificate | 86618.5
Amount certified (excl GST) | 779566.5
GST | 77956.65
Amount payable (incl GST) | 857523.15
Clock
Claim served | 2026-04-25
Certificate due | 2026-05-09 | AS 4000 cl 37.2, counted on the Clock sheet
Reminder | 2026-05-07
Built by Alexios Kavallaris, civil engineer, from the Gnosis sample contract. gnosis.ltd

## Clock
Clock: the date the certificate is due
The claim date comes from the Claim sheet. Change it there and every date here moves. The table on the right holds the public holidays and the end of year window the count skips; add a row if your calendar differs. |  |  |  | Public holidays and shutdown days (date-holidays 3.30.2, public type, 2025 to 2029, plus the end of year window the count skips)
|  |  |  | New South Wales | Victoria
Claim served date (from the Claim sheet) | 2026-04-25 |  |  | 2025-01-01 | 2025-01-01
State (NSW or VIC) | NSW |  |  | 2025-01-27 | 2025-01-27
|  |  |  | 2025-04-18 | 2025-03-10
Rule | Days | Counted in | Due date | 2025-04-19 | 2025-04-18
SOP Act 1999 (NSW) s 14(4): Building and Construction Industry Security of Payment Act 1999 (NSW) s 14(4) (the Act) | 10 | business days | 2026-05-11 | 2025-04-20 | 2025-04-19
SOP Act 2002 (Vic) s 15(4): Building and Construction Industry Security of Payment Act 2002 (Vic) s 15(4) (the Act) | 10 | business days | 2026-05-08 | 2025-04-21 | 2025-04-20
AS 4000 cl 37.2: AS 4000-1997 cl 37.2 (the standard form; your contract may amend it) | 14 | calendar days | 2026-05-09 | 2025-04-25 | 2025-04-21
|  |  |  | 2025-06-09 | 2025-04-25
Schedule or certificate due (the earliest date governs) | 2026-05-09 |  |  | 2025-10-06 | 2025-06-09
Reminder, two countable days before the due date | 2026-05-07 |  |  | 2025-12-25 | 2025-09-26
|  |  |  | 2025-12-26 | 2025-11-04
How the days are counted |  |  |  | 2025-12-27 | 2025-12-22
New South Wales business days: weekends, New South Wales public holidays and 27 to 31 December are not counted. AS 4000 cl 37.2 counts calendar days, every day of the week. The day of service is not counted. |  |  |  | 2025-12-28 | 2025-12-23
Victoria business days: weekends, Victorian public holidays and, for claims served from 15 April 2026 (Act No. 43/2025), 22 December to 10 January are not counted; a claim served before that date keeps the earlier definition with no end of year window. AS 4000 cl 37.2 counts calendar days, every day of the week. The day of service is not counted. |  |  |  | 2025-12-29 | 2025-12-24
The rule rows and the calendar are the ones the payment schedule date check on the site counts with. Your contract may set its own period; put it in the Days column. |  |  |  | 2025-12-30 | 2025-12-25
|  |  |  | 2025-12-31 | 2025-12-26
|  |  |  | 2026-01-01 | 2025-12-27
|  |  |  | 2026-01-26 | 2025-12-28
|  |  |  | 2026-04-03 | 2025-12-29
|  |  |  | 2026-04-04 | 2025-12-30
|  |  |  | 2026-04-05 | 2025-12-31
|  |  |  | 2026-04-06 | 2026-01-01
|  |  |  | 2026-04-25 | 2026-01-02
|  |  |  | 2026-04-27 | 2026-01-03
|  |  |  | 2026-06-08 | 2026-01-04
|  |  |  | 2026-10-05 | 2026-01-05
|  |  |  | 2026-12-25 | 2026-01-06
|  |  |  | 2026-12-26 | 2026-01-07
|  |  |  | 2026-12-27 | 2026-01-08
|  |  |  | 2026-12-28 | 2026-01-09
|  |  |  | 2026-12-29 | 2026-01-10
|  |  |  | 2026-12-30 | 2026-01-26
|  |  |  | 2026-12-31 | 2026-03-09
|  |  |  | 2027-01-01 | 2026-04-03
|  |  |  | 2027-01-26 | 2026-04-04
|  |  |  | 2027-03-26 | 2026-04-05
|  |  |  | 2027-03-27 | 2026-04-06
|  |  |  | 2027-03-28 | 2026-04-25
|  |  |  | 2027-03-29 | 2026-06-08
|  |  |  | 2027-04-25 | 2026-09-25
|  |  |  | 2027-04-26 | 2026-11-03
|  |  |  | 2027-06-14 | 2026-12-22
|  |  |  | 2027-10-04 | 2026-12-23
|  |  |  | 2027-12-25 | 2026-12-24
|  |  |  | 2027-12-26 | 2026-12-25
|  |  |  | 2027-12-27 | 2026-12-26
|  |  |  | 2027-12-28 | 2026-12-27
|  |  |  | 2027-12-29 | 2026-12-28
|  |  |  | 2027-12-30 | 2026-12-29
|  |  |  | 2027-12-31 | 2026-12-30
|  |  |  | 2028-01-01 | 2026-12-31
|  |  |  | 2028-01-03 | 2027-01-01
|  |  |  | 2028-01-26 | 2027-01-02
|  |  |  | 2028-04-14 | 2027-01-03
|  |  |  | 2028-04-15 | 2027-01-04
|  |  |  | 2028-04-16 | 2027-01-05
|  |  |  | 2028-04-17 | 2027-01-06
|  |  |  | 2028-04-25 | 2027-01-07
|  |  |  | 2028-06-12 | 2027-01-08
|  |  |  | 2028-10-02 | 2027-01-09
|  |  |  | 2028-12-25 | 2027-01-10
|  |  |  | 2028-12-26 | 2027-01-26
|  |  |  | 2028-12-27 | 2027-03-08
|  |  |  | 2028-12-28 | 2027-03-26
|  |  |  | 2028-12-29 | 2027-03-27
|  |  |  | 2028-12-30 | 2027-03-28
|  |  |  | 2028-12-31 | 2027-03-29
|  |  |  | 2029-01-01 | 2027-04-25
|  |  |  | 2029-01-26 | 2027-06-14
|  |  |  | 2029-03-30 | 2027-09-24
|  |  |  | 2029-03-31 | 2027-11-02
|  |  |  | 2029-04-01 | 2027-12-22
|  |  |  | 2029-04-02 | 2027-12-23
|  |  |  | 2029-04-25 | 2027-12-24
|  |  |  | 2029-06-11 | 2027-12-25
|  |  |  | 2029-10-01 | 2027-12-26
|  |  |  | 2029-12-25 | 2027-12-27
|  |  |  | 2029-12-26 | 2027-12-28
|  |  |  | 2029-12-27 | 2027-12-29
|  |  |  | 2029-12-28 | 2027-12-30
|  |  |  | 2029-12-29 | 2027-12-31
|  |  |  | 2029-12-30 | 2028-01-01
|  |  |  | 2029-12-31 | 2028-01-02
2028-01-03
2028-01-04
2028-01-05
2028-01-06
2028-01-07
2028-01-08
2028-01-09
2028-01-10
2028-01-26
2028-03-13
2028-04-14
2028-04-15
2028-04-16
2028-04-17
2028-04-25
2028-06-12
2028-09-29
2028-11-07
2028-12-22
2028-12-23
2028-12-24
2028-12-25
2028-12-26
2028-12-27
2028-12-28
2028-12-29
2028-12-30
2028-12-31
2029-01-01
2029-01-02
2029-01-03
2029-01-04
2029-01-05
2029-01-06
2029-01-07
2029-01-08
2029-01-09
2029-01-10
2029-01-26
2029-03-12
2029-03-30
2029-03-31
2029-04-01
2029-04-02
2029-04-25
2029-06-11
2029-09-28
2029-11-06
2029-12-22
2029-12-23
2029-12-24
2029-12-25
2029-12-26
2029-12-27
2029-12-28
2029-12-29
2029-12-30
2029-12-31
2030-01-01
2030-01-02
2030-01-03
2030-01-04
2030-01-05
2030-01-06
2030-01-07
2030-01-08
2030-01-09
2030-01-10
Built by Alexios Kavallaris, civil engineer, from the Gnosis sample contract. gnosis.ltd

## Notes
Where every example figure comes from
Every figure in this workbook is read from the sample contract's own documents and seed. Nothing is typed from memory. A spaced hyphen in a source description is written as a comma.
Cell | What | Source
Claim!B4 | Contract | sandbox-seed-au.plan.ts, SANDBOX_AU_CONTRACT_DTO (the Queensland sample, carried as the worked example; the clock rows are the NSW and Victorian ones)
Claim!B5 | Contract number | sandbox-seed-au.plan.ts, SANDBOX_AU_CONTRACT_DTO (the Queensland sample, carried as the worked example; the clock rows are the NSW and Victorian ones)
Claim!B6 | Principal | sandbox-seed-au.plan.ts, SANDBOX_AU_CONTRACT_DTO (the Queensland sample, carried as the worked example; the clock rows are the NSW and Victorian ones)
Claim!B7 | Contractor | sandbox-seed-au.plan.ts, SANDBOX_AU_CONTRACT_DTO (the Queensland sample, carried as the worked example; the clock rows are the NSW and Victorian ones)
Claim!B8 | Superintendent | sandbox-seed-au.plan.ts, SANDBOX_AU_CONTRACT_DTO (the Queensland sample, carried as the worked example; the clock rows are the NSW and Victorian ones)
Claim!B9 | General conditions | sandbox-seed-au.plan.ts, SANDBOX_AU_CONTRACT_DTO (the Queensland sample, carried as the worked example; the clock rows are the NSW and Victorian ones)
Claim!B10 | Currency | BCE_Bill_of_Quantities.xlsx row 10
Claim!B11 | Claim number | BCE_Progress_Claim_No2.xlsx, claim 2
Claim!B12 | Claim date (the example) | BCE_Progress_Claim_No2.xlsx row 14 (DATE)
Claim!B14 | GST rate | BCE_Progress_Claim_No2.xlsx row 48, Goods and Services Tax (GST @ 10%)
Claim!B15 to B16 | Retention | sandbox-seed-au.plan.ts, SANDBOX_AU_CONTRACT_DTO retentionUpToPercentage 10, retentionMaxValue 423000 (the Queensland sample's terms, carried as the worked example for the two southern states)
Claim!A20 to E20 | Item 1.01: item, description, unit, quantity, rate | BCE_Bill_of_Quantities.xlsx row 14, columns A to E (the contract amount in F is quantity times rate, the same as column F of the source)
Claim!G20 | Item 1.01: previously certified percent | BCE_Progress_Claim_No2.xlsx row 24, column I (previously claimed) divided by column F (contract amount)
Claim!H20 | Item 1.01: claimed to date percent | BCE_Progress_Claim_No2.xlsx row 24, column G (percent complete to date)
Claim!A21 to E21 | Item 1.02: item, description, unit, quantity, rate | BCE_Bill_of_Quantities.xlsx row 15, columns A to E (the contract amount in F is quantity times rate, the same as column F of the source)
Claim!G21 | Item 1.02: previously certified percent | BCE_Progress_Claim_No2.xlsx row 25, column I (previously claimed) divided by column F (contract amount)
Claim!H21 | Item 1.02: claimed to date percent | BCE_Progress_Claim_No2.xlsx row 25, column G (percent complete to date)
Claim!A22 to E22 | Item 2.01: item, description, unit, quantity, rate | BCE_Bill_of_Quantities.xlsx row 20, columns A to E (the contract amount in F is quantity times rate, the same as column F of the source)
Claim!G22 | Item 2.01: previously certified percent | BCE_Progress_Claim_No2.xlsx row 30, column I (previously claimed) divided by column F (contract amount)
Claim!H22 | Item 2.01: claimed to date percent | BCE_Progress_Claim_No2.xlsx row 30, column G (percent complete to date)
Claim!A23 to E23 | Item 2.02: item, description, unit, quantity, rate | BCE_Bill_of_Quantities.xlsx row 21, columns A to E (the contract amount in F is quantity times rate, the same as column F of the source)
Claim!G23 | Item 2.02: previously certified percent | BCE_Progress_Claim_No2.xlsx row 31, column I (previously claimed) divided by column F (contract amount)
Claim!H23 | Item 2.02: claimed to date percent | BCE_Progress_Claim_No2.xlsx row 31, column G (percent complete to date)
Claim!A24 to E24 | Item 2.03: item, description, unit, quantity, rate | BCE_Bill_of_Quantities.xlsx row 22, columns A to E (the contract amount in F is quantity times rate, the same as column F of the source)
Claim!G24 | Item 2.03: previously certified percent | BCE_Progress_Claim_No2.xlsx row 32, column I (previously claimed) divided by column F (contract amount)
Claim!H24 | Item 2.03: claimed to date percent | BCE_Progress_Claim_No2.xlsx row 32, column G (percent complete to date)
Claim!A25 to E25 | Item 3.01: item, description, unit, quantity, rate | BCE_Bill_of_Quantities.xlsx row 25, columns A to E (the contract amount in F is quantity times rate, the same as column F of the source)
Claim!G25 | Item 3.01: previously certified percent | BCE_Progress_Claim_No2.xlsx row 35, column I (previously claimed) divided by column F (contract amount)
Claim!H25 | Item 3.01: claimed to date percent | BCE_Progress_Claim_No2.xlsx row 35, column G (percent complete to date)
Claim!A26 to E26 | Item 3.02: item, description, unit, quantity, rate | BCE_Bill_of_Quantities.xlsx row 26, columns A to E (the contract amount in F is quantity times rate, the same as column F of the source)
Claim!G26 | Item 3.02: previously certified percent | BCE_Progress_Claim_No2.xlsx row 36, column I (previously claimed) divided by column F (contract amount)
Claim!H26 | Item 3.02: claimed to date percent | BCE_Progress_Claim_No2.xlsx row 36, column G (percent complete to date)
Claim!A27 to E27 | Item 3.03: item, description, unit, quantity, rate | BCE_Bill_of_Quantities.xlsx row 27, columns A to E (the contract amount in F is quantity times rate, the same as column F of the source)
Claim!G27 | Item 3.03: previously certified percent | BCE_Progress_Claim_No2.xlsx row 37, column I (previously claimed) divided by column F (contract amount)
Claim!H27 | Item 3.03: claimed to date percent | BCE_Progress_Claim_No2.xlsx row 37, column G (percent complete to date)
Claim!A28 to E28 | Item 4.01: item, description, unit, quantity, rate | BCE_Bill_of_Quantities.xlsx row 31, columns A to E (the contract amount in F is quantity times rate, the same as column F of the source)
Claim!G28 | Item 4.01: previously certified percent | BCE_Progress_Claim_No2.xlsx row 41, column I (previously claimed) divided by column F (contract amount)
Claim!H28 | Item 4.01: claimed to date percent | BCE_Progress_Claim_No2.xlsx row 41, column G (percent complete to date)
Claim!A29 to E29 | Item 4.03: item, description, unit, quantity, rate | BCE_Bill_of_Quantities.xlsx row 33, columns A to E (the contract amount in F is quantity times rate, the same as column F of the source)
Claim!G29 | Item 4.03: previously certified percent | BCE_Progress_Claim_No2.xlsx row 43, column I (previously claimed) divided by column F (contract amount)
Claim!H29 | Item 4.03: claimed to date percent | BCE_Progress_Claim_No2.xlsx row 43, column G (percent complete to date)
Clock!A8 to D8 | SOP Act 1999 (NSW) s 14(4), 10 business days | the rulebook's statutory timeframe seed row AU-NSW-SOPA-S14-PAYMENT-SCHEDULE (Building and Construction Industry Security of Payment Act 1999 (NSW) s 14(4)), as the site's clock-math.mjs holds it
Clock!A9 to D9 | SOP Act 2002 (Vic) s 15(4), 10 business days | the rulebook's statutory timeframe seed row AU-VIC-SOPA-S15-PAYMENT-SCHEDULE (Building and Construction Industry Security of Payment Act 2002 (Vic) s 15(4)), as the site's clock-math.mjs holds it
Clock!A10 to D10 | AS 4000 cl 37.2, 14 calendar days | the rulebook's statutory timeframe seed row AS4000-1997-37-2-PROGRESS-CERTIFICATE (AS 4000-1997 cl 37.2), as the site's clock-math.mjs holds it
Clock!G4 onwards | Public holidays and shutdown days | the site's clock-holidays.json (date-holidays 3.30.2, public type, 2025 to 2029) plus every day of the end of year window the rulebook's calendar profile excludes: New South Wales 12/27 to 12/31 (month/day); Victoria 12/22 to 01/10 (month/day)
Clock!H4 onwards | Victoria end of year window | applies to claims served from 15 April 2026 (Act No. 43/2025); a claim served before that date keeps the earlier definition with no end of year window
Certificate!D10 to D19 | Certified to date | starts equal to the claimed figure on each line; the certifier changes it and writes the reason
Built by Alexios Kavallaris, civil engineer, from the Gnosis sample contract. gnosis.ltd